## Test summary report
Tester | LNSCat, NPTai, BNKNhi, NLAChi
Date | 26/12/2023

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Misalignment of error/success message | The display of error/success messages is misaligned with the message box. | UC001, UC002 | Low | LNSCat | 15/12/2023 | Closed | Fixed
B002 | Can registered with invalid format of email | System displays message that user has registered successfully but because email does not exist so the verification email is not sent and customer cannot verify to register | UC001 | High | LNSCat | 15/12/2023 | Closed | Fixed
B003 | Can registered with invalid format of phone number | System displays message that user has registered successfully. However, he phone number does not exist so the restaurant cannot contact with customer | UC001 | High | LNSCat | 15/12/2023 | Closed | Fixed
B004 | Insert new user despite entering invalid email/phone number | System displays message that there are errors in format of email/phone number. However, the user information is still inserted to database | UC001 | Medium | LNSCat | 2024-06-01 | Closed | Fixed
B005 | Searching with similar word do not found result reservation | System do not show the reservation have similar name to the search words | UC05 | Medium | BNKNhi | 2024-04-01 | Open
B005 | Invalid input for ordering food. | After choosing a dish, the requirement were filled without any checking progress.· | UC04 | Low | NLAChi | 2024-06-01 | Closed
B006 | Cannot cancel the mistaken orders. | The requirements were filled in with the incorrect information about the food from the customer. | UC04 | Medium | NLAChi | 2024-06-01 | Open
B007 | There is no notification when adjusting information without pressing a button | The user adjusts or adds information to the corresponding form, but does not click update or add to save changes, or redirects to another page, the system does not issue a reminder before navigating. | UC05 | Low | BNKNhi | 2024-06-01 | Open
B008 | Unknown alert message display when logging as customer | When logging as a customer, error and success alert display with no message | UC02 | Low | LNSCat | 2024-07-01 | Closed | Fixed